NAME: SRUTI VERMA

REGISTARTION NO:18BCE1005

EVA

EV = Earned Value

PV = Planned Value

BAC = Budget at Completion

AC = Actual Cost

PV = Planned Completion (%) * BAC

EV = Actual Completion (%) * BAC

CPI = EV/AC

SPI = EV/PV

Suppose our project has a budgeted cost  at 50,00,000 rupees. The project is to be completed in 3 months. After a month, we have completed 30 percent of the project at a total expense of 80,00,000 rupees. The planned completion should have been 40 percent.

From the scenario, you can extract the following:

- BAC = 50,00,000

- AC = 80,00,000.

The Planned Value (PV) and Earned Value (EV) can then be computed as follows:

- Planned Value = Planned Completion (%) * BAC = 40% * 50,00,000 =20,00,000

- Earned Value = Actual Completion (%) * BAC = 30% * 50,00,000 = 15,00,000

Compute the earned value variances:

- Cost Performance Index (CPI) = EV / AC = 15,00,000

- / 80,00,000 = 0.1875  . This means for every 1rupee spent, the project is producing only 0.1875 paise in work.

- Schedule Performance Index (SPI) = EV / PV = 15,00,000 /20,00,000 = 0.75 . This means for every estimated hour of work, the project team is completing only 0.75 hours.

Interpretation: Since both Cost Performance Index (CPI index) and Schedule Performance Index (SPI index) are less than 1, it means that the project is over budget and behind schedule. This  project is in major trouble and corrective action needs to be taken.

#include<stdio.h>

int main()

{

float AC,BAC,PC,ACTUALcom,EARNED_VALUE,PLANNED_VALUE;

float CPI,SPI;

printf("enter total expense :\n");

scanf("%f",&AC);

printf("enter budegeted cost of project :\n");

scanf("%f",&BAC);

printf("enter planned completion in percentage:\n");

scanf("%f",&PC);

printf("enter actual completion in percentage:\n");

scanf("%f",&ACTUALcom);

PLANNED_VALUE=PC*BAC;

EARNED_VALUE=ACTUALcom*BAC;

CPI=EARNED_VALUE/AC;

SPI=EARNED_VALUE/PLANNED_VALUE;

printf("the cost performance index is %f \n",CPI);

printf("the schedule performance index is %f ",SPI);

}

OUTPUT:

enter total expense in lacs:

8000000

enter budegeted cost of project in lacs:

5000000

enter planned completion in percentage:

0.4

enter actual completion in percentage:

0.3

the cost performance index is 0.187500

the schedule performance index is 0.750000